Program of Work for Sierra Nevada Public Lands Management Act

Robert Scheller, Associate Professor, Portland State University

Alec Kretchun, Research Staff, Portland State University

October 10, 2016

This program of work describes anticipated accomplishments and deliverables for the initial phase of the third Sierra Nevada Public Lands Management Agency (SNPLMA) Lake Tahoe project for Portland State University. This project extends previous LANDIS-II modeling work done in the Lake Tahoe Basin to include new modeling scenarios, make explicit linkages to the science team, improve fire modeling under climate change, and tightly integrate hydrology.

*Staff and responsibilities*

Staff at Portland State University include:

Dr Robert Scheller, Associate Professor – will act as PI and project supervisor, and coordinate modeling efforts with project collaborators

Alec Kretchun, research staff – will act as day-to-day project manager, acquire necessary data, run LANDIS-II models, and analyze output

*Timeline*

Anticipated start date for this program of work is December 1, 2016 and is projected to last until April 30, 2016.

*Project Initialization and model evaluation*

This project leverages two previous rounds of LANDIS-II modeling in the Lake Tahoe Basin, much of which has now appears in published manuscripts. However, many model developments and innovations have taken place since the most recent simulations were completed. So, one of the first tasks to evaluate if any of the previous input parameters need to be updated to reflect the updates to the model architecture. Once a thorough evaluation of input parameters has been completed, simulations will be run with historic climate to further assess the need for updates to previously vetted input parameter values.

*Climate Data Acquisition and Management*

One of the major LANDIS-II model developments since the completion of the previous SNPLMA project is the tight coordination of climate data across all model processes, as managed by the NECN model extension and climate library. For the initial project phase, we will work with local collaborators to determine which climate change scenarios are most applicable and meaningful for the science and management teams, in order to project a range of anticipated ecological outcomes. We will then acquire data for these climate change scenarios and organize it for use within the climate library.

*Model Scenario Development*

One of the major proposed accomplishments of this project is to include new management scenarios that encompass fuel treatments beyond the Wildland Urban Interface (WUI). Prior research limited simulated management to areas immediately within or adjacent to the WUI, consistent with previous management plans. In this initial project phase we will design these scenarios through a highly collaborative process with local scientists and managers. Effective model scenario development is critical to the success of LANDIS-II as a centralized platform to serve data relevant to many ongoing research efforts including hydrology, smoke modeling, erosion, bird habitat, etc. In addition, a new initiative to expand treatments beyond the WUI will benefit from carefully designed simulations of effectiveness (measured as reduction of fire risk) and consequences for other ecosystem services.

*Project Meeting*

A project meeting is scheduled for January, to be held in South Lake Tahoe. Dr. Scheller and Alec will attend this meeting in order to meet all project participants and have breakout sessions on climate change projections and scenario development.